## From Site 1
S.N | Description | Villa Diamond |  | الكميات المنفذة منذ بدء المشروع و حتي 31/7 |  |  |  |  | نسب الصرف
|  | BOQ QTY | Unit | Supply | 1 st Fix | 2 nd Fix | 3rd Fix | Test & Comm. | Supply | 1 st Fix | 2 nd Fix | 3rd Fix | Test & Comm. | QTY | %
Division 26 - ELECTRICAL
SECTION 260519 LOW VOLTAGE POWER CONDUCTORS AND CABLES
Supply, Install, testing and commissioning and handing over complete conductors and cables work. Manholes Conduits and fittings, draw wires and the like. The Contractor's installation rate includes, without limitation, earth work (excavation & backfill), the supply and installation of termination kit, warning tape, joints, concrete tiles and all accessories, fittings, sealant, builder work, connection, and any other materials or works required for the proper installation.
450/ 750V; single core copper with PVC insulation grounding cables
1 | 1x10mm² | 100 | m | 50 | 0 | 0 | 25 | 0 | 40% | 0% | 0% | 50% | 10% | 50 | 65%
2 | 1x16mm² | 150 | m | 50 | 0 | 0 | 25 | 0 | 40% | 0% | 0% | 50% | 10% | 50 | 65%
450/ 750V; single core Aluminum with PVC insulation grounding cables
3 | 1x16mm² | 100 | m | 30 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 30 | 40%
4 | 1x25mm² | 20 | m | 0 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10%
5 | 1x50mm² | 184 | m | 0 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10%
0.6/ 1 kV; multi- core copper cables with PVC insulation/ PVC sheathed
1 | 4x10mm² | 50 | m | 20 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 20 | 40%
2 | 4x25 mm² | 45 | m | 45 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 45 | 40%
0.6/ 1 kV; multi- core Aluminum cables with XLPE insulation/ PVC sheathed
3 | 3x95+ 1x50 mm² | 184 | m | 184 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 184 | 40%
4 | 3x50+ 1x25 mm² | 20 | m | 20 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 20 | 40%
5 | 4x16 mm² | 99 | m | 99 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 99 | 40%
SECTION 262300 CABLE TRAYS.
Supply, install, testing and commissioning and handing over complete galvanized steel cable tray /Ladder with supports, clamps, all necessary bends, covers, end plates, elbows and accessories to form a complete system, mounting fittings, including cutting and jointing thereto, jointing between sections, bends, tees, etc., components for earth continuity, adaptors and connections between tray/ladder Trunking and items of equipment or control gear requiring the use of flanges and/or the forming of apertures, pin racks for supporting cable, Supports including fixing.
Hot Dip, Galvanized, Perforated Type Cable Trays.
1 | 150 mm wide, uncovered | 72 | m | 72 | 15 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 72 | 24.17%
Hot Dip, Galvanized, Perforated Type Cable Trunk
2 | 300 mm wide, Low current | 80 | m | 80 | 20 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 80 | 25%
SECTION 262416 PANELBOARDS
Supply, Install , connect , test and commission on the following devices as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification the Contractor's installation rate includes, without limitation, the supply and installation of earthling, cable glands, cables termination and all accessories, fittings, sealant, builder work, electric connection, and any other materials or works required for the proper installation as required in design and contract packages."
1 | MDB | 1 | nr | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5%
2 | EMDB | 1 | nr | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5%
3 | Digital KWHM | 2 | nr | 2 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 2 | 20%
SECTION 262726 WIRING DEVICES
Supply, Install , connect , test, commission and handing over on the following devices as specified and indicated on Drawings including includes; back box, wires, including protective earthing conductors, termination, conduits, conduits fittings, Trunking and other raceways, accessories and fillings from lighting switch to final branch circuit panelboard and all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification "The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation".
1 | General lighting switch type one way, one gang | 10 | nr | 10 | 10 |  |  |  | 0% | 20% | 30% | 45% | 5% | 10 | 20%
2 | General lighting switch type one way, two gangs | 8 | nr | 8 | 8 |  |  |  | 0% | 20% | 30% | 45% | 5% | 8 | 20%
3 | General lighting switch type two way, one gang | 6 | nr | 6 | 6 |  |  |  | 0% | 20% | 30% | 45% | 5% | 6 | 20%
4 | General lighting switch type one way, one gang, weather proof | 4 | nr | 4 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 4 | 20%
5 | General lighting switch type two way, one gang, weather proof | 4 | nr | 4 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 4 | 20%
Sockets outlets.
Supply, install, testing and commissioning and handing over Socket outlet, Exhaust outlet and Electrical outlet includes; back box, wires, including protective earthing conductors, termination, conduits, conduits fittings, Trunking and other raceways, accessories and fittings from socket outlet to final branch circuit panelboard, as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification ''The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation."
1 | Electric outlet | 10 | nr | 8 | 5 |  |  |  | 0% | 20% | 30% | 45% | 5% | 8 | 12.5%
2 | General use single socket | 15 | nr | 10 | 5 |  |  |  | 0% | 20% | 30% | 45% | 5% | 10 | 10%
3 | General use duplex socket | 8 | nr | 8 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 8 | 10%
SECTION 262816 ENCLOSED SWITCHES AND CIRCUIT BREAKERS
Supply, Install, testing and commissioning and handing over complete enclosed switches and circuit breakers with all necessary accessories and ancillary works, as specified and as shown in drawings, wires or cables including protective earthing conductors, conduits, trays, Trunking and other raceways (Where trays, ladders or conduits are not measured separately) and fittings from outlet to motor control centers or panels or to low voltage board, fixing and supporting material.
1 | 25 A: two pole, weather proof | 3 | nr | 3 | 3 |  |  |  | 0% | 20% | 30% | 45% | 5% | 3 | 20%
2 | 32 A: two pole, weather proof | 2 | nr | 2 | 2 |  |  |  | 0% | 20% | 30% | 45% | 5% | 2 | 20%
3 | 40 A: two pole, weather proof | 1 | nr | 1 | 1 |  |  |  | 0% | 20% | 30% | 45% | 5% | 1 | 20%
SECTION 265113 - INTERIOR LIGHTING
Supply, install testing and commissioning and handing over lighting fixture outlet includes; boxes, wires including protective earthing conductors, termination, conduits, Trunking and other raceways, accessories and fittings from outlet to next outlet or to final branch circuit panelboard.
1 | Lighting Fixture Outlet | 70 | nr | 35 | 30 |  |  |  | 0% | 20% | 30% | 45% | 5% | 35 | 17.14%
Supply, Install , connect , test and commission on the following devices as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification "The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation in order to hand over this item in a functional and operable conditions as required in design and contract packages."
1 | Type F1 | 50 | nr | 0 |  |  |  |  | 40% | 0% | 0% | 55% | 5%
2 | Type F2 | 20 | nr | 0 |  |  |  |  | 40% | 0% | 0% | 55% | 5%
Division 27 - COMMUNICATION SYSTEMS
SECTION 271000 : STRUCTURED CABLING NETWORK
Data , Voice And TV Outlets
supply , install outlet including boxes, Cat 6 cables inside pvc conduits, cable termination, conduits, conduits fittings, raceways, all necessary accessories and ancillary works and materials required for complete installations from outlet to main or horizontal communication cabinet including fittings, accessories and all associated and ancillary works and supports
1 | Voice/Data/TV outlets | 12 | nr | 12 | 12 |  |  |  | 0% | 20% | 30% | 45% | 5% | 12 | 20%

## BOQ
S.N | Description | Villa Diamond |  | الكميات المنفذة منذ بدء المشروع و حتي 31/7 |  |  |  |  | نسب الصرف | [5 empty] | سابق |  |  | حالي |  |  | اجمالــي
|  | BOQ QTY | Unit | Supply | 1 st Fix | 2 nd Fix | 3rd Fix | Test & Comm. | Supply | 1 st Fix | 2 nd Fix | 3rd Fix | Test & Comm. | Rate | اجمالي | % | كمية | اجمالي | % | كمية | اجمالي | كمية
Division 26 - ELECTRICAL
SECTION 260519 LOW VOLTAGE POWER CONDUCTORS AND CABLES
Supply, Install, testing and commissioning and handing over complete conductors and cables work. Manholes Conduits and fittings, draw wires and the like. The Contractor's installation rate includes, without limitation, earth work (excavation & backfill), the supply and installation of termination kit, warning tape, joints, concrete tiles and all accessories, fittings, sealant, builder work, connection, and any other materials or works required for the proper installation.
450/ 750V; single core copper with PVC insulation grounding cables
1 | 1x10mm² | 100 | m | 50 | 0 | 0 | 25 | 0 | 40% | 0% | 0% | 50% | 10% | 300 | 0 | 0 | 0 | 9750 | 65% | 50 | 9750 | 50
2 | 1x16mm² | 150 | m | 50 | 0 | 0 | 25 | 0 | 40% | 0% | 0% | 50% | 10% | 400 | 0 | 0 | 0 | 13000 | 65% | 50 | 13000 | 50
| 450/ 750V; single core Aluminum with PVC insulation grounding cables | [20 empty] | 0
3 | 1x16mm² | 100 | m | 30 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 150 | 0 | 0 | 0 | 1800 | 40% | 30 | 1800 | 30
4 | 1x25mm² | 20 | m | 0 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 160 | 0 | 0 | 0
5 | 1x50mm² | 184 | m | 0 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 260 | 0 | 0 | 0
0.6/ 1 kV; multi- core copper cables with PVC insulation/ PVC sheathed
1 | 4x10mm² | 50 | m | 20 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 500 | 0 | 0 | 0 | 4000 | 40% | 20 | 4000 | 20
2 | 4x25 mm² | 45 | m | 45 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 750 | 0 | 0 | 0 | 13500 | 40% | 45 | 13500 | 45
0.6/ 1 kV; multi- core Aluminum cables with XLPE insulation/ PVC sheathed
3 | 3x95+ 1x50 mm² | 184 | m | 184 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 2000 | 0 | 0 | 0 | 147200 | 40% | 184 | 147200 | 184
4 | 3x50+ 1x25 mm² | 20 | m | 20 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 1650 | 0 | 0 | 0 | 13200 | 40% | 20 | 13200 | 20
5 | 4x16 mm² | 99 | m | 99 | 0 | 0 | 0 | 0 | 40% | 0% | 0% | 50% | 10% | 1100 | 0 | 0 | 0 | 43560 | 40% | 99 | 43560 | 99
SECTION 262300 CABLE TRAYS.
Supply, install, testing and commissioning and handing over complete galvanized steel cable tray /Ladder with supports, clamps, all necessary bends, covers, end plates, elbows and accessories to form a complete system, mounting fittings, including cutting and jointing thereto, jointing between sections, bends, tees, etc., components for earth continuity, adaptors and connections between tray/ladder Trunking and items of equipment or control gear requiring the use of flanges and/or the forming of apertures, pin racks for supporting cable, Supports including fixing.
Hot Dip, Galvanized, Perforated Type Cable Trays.
1 | 150 mm wide, uncovered | 72 | m | 72 | 15 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 536 | 0 | 0 | 0 | 9326.4 | 24.17% | 72 | 9326.4 | 72
| Hot Dip, Galvanized, Perforated Type Cable Trunk | [20 empty] | 0
2 | 300 mm wide, Low current | 80 | m | 80 | 20 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 804 | 0 | 0 | 0 | 16080 | 25% | 80 | 16080 | 80
SECTION 262416 PANELBOARDS
Supply, Install , connect , test and commission on the following devices as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification the Contractor's installation rate includes, without limitation, the supply and installation of earthling, cable glands, cables termination and all accessories, fittings, sealant, builder work, electric connection, and any other materials or works required for the proper installation as required in design and contract packages."
1 | MDB | 1 | nr | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 100000 | 0 | 0 | 0
2 | EMDB | 1 | nr | 0 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 75000 | 0 | 0 | 0
3 | Digital KWHM | 2 | nr | 2 | 0 | 0 | 0 | 0 | 20% | 20% | 0% | 55% | 5% | 30000 | 0 | 0 | 0 | 12000 | 20% | 2 | 12000 | 2
SECTION 262726 WIRING DEVICES
Supply, Install , connect , test, commission and handing over on the following devices as specified and indicated on Drawings including includes; back box, wires, including protective earthing conductors, termination, conduits, conduits fittings, Trunking and other raceways, accessories and fillings from lighting switch to final branch circuit panelboard and all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification "The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation".
1 | General lighting switch type one way, one gang | 10 | nr | 10 | 10 |  |  |  | 0% | 20% | 30% | 45% | 5% | 414 | 0 | 0 | 0 | 828 | 20% | 10 | 828 | 10
2 | General lighting switch type one way, two gangs | 8 | nr | 8 | 8 |  |  |  | 0% | 20% | 30% | 45% | 5% | 539 | 0 | 0 | 0 | 862.4 | 20% | 8 | 862.4 | 8
3 | General lighting switch type two way, one gang | 6 | nr | 6 | 6 |  |  |  | 0% | 20% | 30% | 45% | 5% | 664 | 0 | 0 | 0 | 796.8 | 20% | 6 | 796.8 | 6
4 | General lighting switch type one way, one gang, weather proof | 4 | nr | 4 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 726 | 0 | 0 | 0 | 580.8 | 20% | 4 | 580.8 | 4
5 | General lighting switch type two way, one gang, weather proof | 4 | nr | 4 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 164 | 0 | 0 | 0 | 131.2 | 20% | 4 | 131.2 | 4
| Sockets outlets. | [13 empty] | 0 | 0 | 0
Supply, install, testing and commissioning and handing over Socket outlet, Exhaust outlet and Electrical outlet includes; back box, wires, including protective earthing conductors, termination, conduits, conduits fittings, Trunking and other raceways, accessories and fittings from socket outlet to final branch circuit panelboard, as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification ''The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation."
1 | Electric outlet | 10 | nr | 8 | 5 |  |  |  | 0% | 20% | 30% | 45% | 5% | 1085 | 0 | 0 | 0 | 1085 | 12.5% | 8 | 1085 | 8
2 | General use single socket | 15 | nr | 10 | 5 |  |  |  | 0% | 20% | 30% | 45% | 5% | 1322 | 0 | 0 | 0 | 1322 | 10% | 10 | 1322 | 10
3 | General use duplex socket | 8 | nr | 8 | 4 |  |  |  | 0% | 20% | 30% | 45% | 5% | 4768 | 0 | 0 | 0 | 3814.4 | 10% | 8 | 3814.4 | 8
SECTION 262816 ENCLOSED SWITCHES AND CIRCUIT BREAKERS
Supply, Install, testing and commissioning and handing over complete enclosed switches and circuit breakers with all necessary accessories and ancillary works, as specified and as shown in drawings, wires or cables including protective earthing conductors, conduits, trays, Trunking and other raceways (Where trays, ladders or conduits are not measured separately) and fittings from outlet to motor control centers or panels or to low voltage board, fixing and supporting material.
1 | 25 A: two pole, weather proof | 3 | nr | 3 | 3 |  |  |  | 0% | 20% | 30% | 45% | 5% | 1161 | 0 | 0 | 0 | 696.6 | 20% | 3 | 696.6 | 3
2 | 32 A: two pole, weather proof | 2 | nr | 2 | 2 |  |  |  | 0% | 20% | 30% | 45% | 5% | 2411 | 0 | 0 | 0 | 964.4 | 20% | 2 | 964.4 | 2
3 | 40 A: two pole, weather proof | 1 | nr | 1 | 1 |  |  |  | 0% | 20% | 30% | 45% | 5% | 2411 | 0 | 0 | 0 | 482.2 | 20% | 1 | 482.2 | 1
| SECTION 265113 - INTERIOR LIGHTING | [13 empty] | 0 | 0 | 0
Supply, install testing and commissioning and handing over lighting fixture outlet includes; boxes, wires including protective earthing conductors, termination, conduits, Trunking and other raceways, accessories and fittings from outlet to next outlet or to final branch circuit panelboard.
1 | Lighting Fixture Outlet | 70 | nr | 35 | 30 |  |  |  | 0% | 20% | 30% | 45% | 5% | 803 | 0 | 0 | 0 | 4818 | 17.14% | 35 | 4818 | 35
Supply, Install , connect , test and commission on the following devices as specified and indicated on Drawings including all necessary accessories and fitting required to complete the work according to design and relevant section of division 26 of the specification "The Contractor's installation rate includes, without limitation, the supply and installation of all accessories, fittings, sealant, civil & builder work, electric connection, and any other materials or works required for the proper installation in order to hand over this item in a functional and operable conditions as required in design and contract packages."
1 | Type F1 | 50 | nr | 0 |  |  |  |  | 40% | 0% | 0% | 55% | 5% | 1000 | 0 | 0 | 0
2 | Type F2 | 20 | nr | 0 |  |  |  |  | 40% | 0% | 0% | 55% | 5% | 1100 | 0 | 0 | 0
Division 27 - COMMUNICATION SYSTEMS
SECTION 271000 : STRUCTURED CABLING NETWORK
Data , Voice And TV Outlets
supply , install outlet including boxes, Cat 6 cables inside pvc conduits, cable termination, conduits, conduits fittings, raceways, all necessary accessories and ancillary works and materials required for complete installations from outlet to main or horizontal communication cabinet including fittings, accessories and all associated and ancillary works and supports
1 | Voice/Data/TV outlets | 12 | nr | 12 | 12 |  |  |  | 0% | 20% | 30% | 45% | 5% | 1506 | 0 | 0 | 0 | 3614.4 | 20% | 12 | 3614.4 | 12
[21 empty] | 303412.6 | 763

## Cover
Insert Logo |  |  | Insert Logo
| Project | Villa
| Contract | Villa
| Owner | Elsaeid Gamal Elsaeid
PM
| Consultant | Moustafa Gamal
| Contractor | Dar Al-Kahrbaa
|  |  |  | Interim Cut Date | 2023-07-31
|  | Interim Payment Certificate | 1 | Payment Date | 2023-07-01

## Summary
Villa
Villa
Interim Payment Certificate
| 0 | DATE : |  |  |  | Villa | CONTRACT No. : 1
Construction of Parcel S1 Residential Buildings. | [6 empty] | CONTRACT :
[6 empty] | Dar Al-Kahrbaa | CONTRACTOR : Ahmed Gamal Elsaeid
2023-08-31 | 2023-08-01 |  | Contract Date From and To : | 1304270 |  |  | Basic Scope
WORK DONE AS OF : 31 Jul 2023
Total Value of Works Executed To End of Invoice Period
DAMAGE REPORTS
303412.6 |  |  | Sub - Total
ADDITIONS / OMISSIONS
-30341.26 |  |  |  | 10 % of Current Invoice | -30341.26 |  | Recovery of advanced payement
-2889.6438 |  |  |  | x 1 % | 288964.381 |  | Less Taxes
-15170.63 |  |  |  | x 5 % | 303412.6 |  | Less Social Insurances
-1820.4756 | [6 empty] | Hold amount due to casual labor forces 0.6%
-910.2378 | [6 empty] | Hold Amount due to EGY.Syndicate of engineers Fees x 0.3 %
0 | [6 empty] | Back charge & Penalties Withheld as per attached
0 | [6 empty] | Previous Payments
252280.3528 | [6 empty] | NET PAYMENT